## Planning
Schedule for Research Plan: Towards assessment strategies for the new Dutch Computer Science secondary education curriculum
Key indicating related Study: |  |  | Last updated: | 2018-10-09
General
I. Algorithms
II. Recontextualization
III. Physical Computing
| Study | Phase | Deliverable / Task | Status
Nov 2017 - Oct 2018 | I, II, III | Research Plan | Research Plan | reviewed
| I, II | Domain Analysis | Algorithms + CT | reviewed
| I, II, III | Literature Research | Review study: Relevant design principles | def
| I, II | Domain Modelling | KSAs for Algorithms + CT | reviewed
Nov 2018 - Dec 2018 | I, II, III | Research Plan | Research Plan | def
| II | Literature Research | Review study Recontextualization | def
| III | Literature Research | Review study Physical Computing | def
| I | Analysis Algorithms: untangling tasks | Analysis of existing tasks | def
| III | Domain Analysis | Physical Computing | reviewed
| II | Conceptual Assessment framework | Algorithms: student+evidence+task models+specifications | concept
| I | Modelling: untangling tasks | Progression Pathway | concept
| I | Assessment Implementation | Example task | concept
| I | Assessment Delivery: pilot small scale | Evaluation of pilot example task | def
| II | Conceptual Assessment framework | Recontextualization: student+evidence+task models+specifications
| II | Assessment Implementation Recontextualization | Example tasks | concept
Jan 2019 - Mar 2019 | II | Assessment Delivery: pilot small scale Recontextualization | Evaluation of pilot example task | def
| III | Domain Modelling | KSAs for Physical Computing | reviewed
| I | Modelling: untangling tasks | Progression Pathway | reviewed
| I | Implementation & Delivery: 2nd pilot untangling tasks | Evaluation of pilot untangling tasks | def
| I | Answer Question 1a | PAPER | def
| III | Conceptual Assessment framework | Phys. Comp: student+evidence+task models+specifications
| II | Instruct teachers on design templates
| II | Small scale pilot Recontextectualization
April 2019 - July 2019 | II | 2nd pilot Recontextualization Assessment Implementation (other teachers) | Tasks made by other teachers | def
| II | 2nd pilot Recontextualization Assessment Delivery (other teachers) | Interviews | def
| II | 2nd pilot Recontextualization Assessment Analysis (other teachers) | Evaluation of task made by other teachers | def
| II | Teacher instruction Recontextualization |  | def
| III | Small scale pilot Physical Computing |  | def
Aug 2019 - Dec 2019 | II | 3rd pilot Recontextualization Assessment Implementation (other teachers) | Tasks made by other teachers | def
| II | 3rd pilot Recontextualization Assessment Delivery (other teachers) | Interviews | def
| II | 3rd pilot Recontextualization Assessment Analysis (other teachers) | Evaluation of task made by other teachers | def
| II | Answer Question 1b | PAPER | def
| II | 2nd pilot Physical Computing | Evaluation of task made by other teachers | def
Jan 2020 - July 2020 | II | 3rd pilot Physical Computing | Evaluation of task made by other teachers | def
| III | Answer Question 2a | PAPER | def
Aug 2020 - Dec 2020 | III | Answer Question 2b | PAPER | def
| III | Deliver PD Physical Computing | insights PCK
Jan 2021 - July 2021 | I, II, III | Answer Question 3 | PAPER | def
Aug 2021 - Dec 2021
Jan 2022 - July 2022
Aug 2022 - Nov 2022

## OUD Planning
Schedule for Research Plan: Towards assessment strategies for the new Dutch Computer Science secondary education curriculum
Key indicating related Study: |  | Last updated: |  | 2018-07-12
General / Preliminary phase
ECD
PCK
Untangling tasks
| Phase | Deliverable / Task | Status | Deadline
Nov 2017 - July 2018 | Planning | Plan | concept | 2018-07-12
| Domain Analysis | Algorithms + CT | concept | 2018-07-12
Aug 2018 - Dec 2018 | Planning | Plan | def | 2018-09-15
| Domain Modelling | KSAs for Algorithms + CT | concept | 2018-09-15
| Literature Research | Review study: Relevant design principles | def | 2018-09-30
| Analysis: untangling tasks | Analysis of existing tasks | def | 2018-09-30
| Domain Analysis | Algorithms + CT | reviewed | 2018-09-30
| Domain Modelling | KSAs for Algorithms + CT | reviewed | 2018-09-30
| Conceptual Assessment framework | student+evidence+task models+specifications | concept | 2018-10-01
| Modelling: untangling tasks | Hierarchy of untangled tasks | concept | 2018-10-15
| Modelling: untangling tasks | Hierarchy of untangled tasks | reviewed | 2018-10-30
| Implementation & Delivery: pilot untangling tasks | Evaluation of pilot untangling tasks | def | 2018-10-30
| Assessment Implementation | Example task | concept | 2018-11-01
| Assessment Delivery: pilot | Evaluation of pilot example task | def | 2018-12-30
| Implementation & Delivery: 2nd pilot untangling tasks | Evaluation of pilot untangling tasks | def | 2018-12-31
Jan 2019 - July 2019 | Assessment Implementation (other teachers) | Tasks made by other teachers | def | 2019-02-01
| Assessment Delivery (other teachers) | Interviews | def | 2019-05-01
|  | Evaluation of task made by other teachers | def | 2019-05-01
| Analysis and evaluation results ECD | Report: lessons learned PCK from ECD exercise | def | 2019-06-01
|  | Report: lessons learned about assessments/students knowledge about algorithms from ECD exercise | def | 2019-06-01
Aug 2019 - Dec 2019
Jan 2020 - July 2020
Aug 2020 - Dec 2020
Jan 2021 - July 2021
Aug 2021 - Dec 2021
Jan 2022 - July 2022
Aug 2022 - Nov 2022